|  | Project Brief |
| --- | --- |

Project Overview

| Project ID | 1505 | Project Name | Estate – External Appearance |
| --- | --- | --- | --- |
| Short Description |
| Refresh the external appearance of all properties (excluding MSCP) across Winterthurway estate. |

Project Governance

| Budget |  | Sponsor | Dave Griffith, Wayne Buckley & Matt Garvey |
| --- | --- | --- | --- |
| Approved on |  | Start Date | Feb ‘15 | End Date | Sep ‘15 |

Project Detail

Purpose & Objectives

To make good the external appearance of all buildings across Winterthur Way. To complete necessary “work at height” maintenance, repairs and renewals concurrent with reinstating the external appearance of all buildings.

Scope

The scope includes all residential blocks and out buildings (e.g.: pumping stations, bike stores, refuse stores) but excludes the multi-storey car park (subject to a separate renewal initiative). Commission surveyor to refresh site survey to determine back-log and near term maintenance needs (aligned to existing planned maintenance schedule documentation); draft specification for all necessary work and propose an anticipated execution approach (e.g.: block sequencing); draft supplier selection criteria (e.g.: least cost etc.) and agree project management approach (e.g.: dedicated oversight from primary contractor etc.). Subject to site survey & surveyors recommendation, scope of work may include, but is not limited to: External cleaning of all properties Completion of any necessary maintenance, repairs & renewals whilst working at height (e.g.: guttering) Renewal of external features (e.g.: painting render in an alternative colour; fixing balconies constructs) Based on agreed specification, obtain quotes and detail description on proposed solutions (e.g.: materials to be used) from relevant vendors; complete due diligence on suppliers and their proposed solutions (e.g.: conduct test cleans of sample areas). Appoint a preferred supplier(s) pending project confirmation; Complete section 20 notice; document contracts (including legal review or warranties, liabilities etc.) and confirm approval to proceed. Confirm work schedule with primary contractor (or suppliers) and communicate schedule of work to all members. Complete all works in accordance with specification; validate / verify completion & quality standard.

Key Milestones (deliverables)

(Specify – Apr 15) Appoint surveyor. Complete site survey refresh & confirm target specification. (Propose - May 15) Obtain supplier estimates for agreed specification. (Consult – Jul 15) Test & confirm proposed solutions; appoint preferred supplier; complete section 20 & confirm approval to proceed. (Implement – Sep 15) Complete external refresh as per specification.