|  | Project Brief |
| --- | --- |

Project Overview

| Project ID | 1508 | Project Name | Site Services Strategy |
| --- | --- | --- | --- |
| Short Description |
| Evaluate alternative strategies for the provision of on-site services (cleaning, light maintenance & repairs and grounds maintenance); subject to business case approval, define and execute a transition plan appropriate to the needs of VHMC. |

Project Governance

| Budget |  | Sponsor | Martin Edge & Wayne Buckley |
| --- | --- | --- | --- |
| Approved on |  | Start Date | Mar ‘15 | End Date | Jun ‘15 |

Project Detail

Purpose & Objectives

To reduce the cost of providing on-site services across the Winterthur way estate. To enable a more flexible approach wrt the planning and execution of light maintenance and repair work. To enhance and project Winterthur Ways identity and image by driving step-change improvement in the quality of works.

Scope

The evaluation (cost & quality) of existing on-site services The identification & specification of future on-site services, which may include, but not be limited to: The provision of a house keeping function responsible for domestic, window & carpet Cleaning The provision of a grounds maintenance service The provision of a non-specialist light maintenance & repair service The identification of alternative approaches for fulfilling site service activity (e.g.: in-source, out-source, single vendor) The development of a business case (to include cost/benefit evaluation of alternative approaches) For the recommended approach, a high level transition plan, to include (by way of example): The specification & approval of any new third party contracts (e.g.: variance to agent terms) The design & delivery of any newly required infrastructure (e.g.: enlarged estate office) The specification and recruitment of any newly required estates staff The procurement of any necessary equipment and/or supplies Subject to formal board approval, execution of the defined transition plan A post implementation review to assure benefit realisation

Key Milestones (deliverables)

(Identify – Mar 15) Evaluate existing and identify future site service needs (Evaluate – Jun 15) Evaluate alternative service delivery options (business case development & review) (Plan – Jul 15) Identify recommended approach & develop transition plan to support its adoption (Execute – Aug 15) Initiate transition of site services to new way of working